## Sheet1
Name of Center: | Africa Center of Excellence for Population Health and Policy
Institution: | Bayero University Kano | [16 empty] | On Schedule
Country | Nigeria
Center Leader: | Prof. Hadiza Galadanci
Annual Workplan (1st Q 2024 - 4th Q 2024) | January 2024 to December 2024
Work Plan Activities | Description |  |  | Q1 2024 |  |  | Q2 2024 |  |  | Q3 2024 |  |  | Q4 2024 |  |  | 2023 Y3Q1 |  |  | 2023 Y4Q2 |  |  | 2023 Y4Q3 |  |  | 2023 Y4Q4 | NOV |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  | Comments | Partner Contributions | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | JAN | FEB | MAR | APRIL | MAY | JUME | JULY | AUG | SEPT | OCT |  | DEC
Action 1: \ DLI Action: Quality Education
Sub-Action 1a: Support E learning
Activity 1: Stepdown Training for faculty to develop online course contents (Harvard Training) | The Center shall facilitate the training of faculty from constituents departments on modalities of develpoing online modules | [28 empty] | 53902 |  |  | Center Team &IT Team | bar: Q1 2024 Jan to Q2 2024 Jun
Sub-Action 1b: Recruitment of regional students
Activity 1: Provision of English language course | Provide English language tutoring in collaboration with English deprtment of the University for francophone students | [28 empty] | 4444 |  |  | Center team
Activity 2: Sponsorship for regional students (stipend, accomodation, tuition and resident permit expenses) | Provide full sponsorship (tuition, accomodation, airfare, monthly stipends and research support) for regional students | [28 empty] | 153407 | 135000 |  | Center Team
Activity 3: Research support for MSc students | Provide research grants for national students' research and dissertation ( 40 new MSc candidates) | [28 empty] | 188570 |  |  | Center Team
Activity 4: Research support for PhD students | Provide research grants for PhD students' research and dissertation (16 PhD candidates) | [28 empty] | 18670
Sub-Action 1c: Short courses
Activity 1: Capacity building for Faculty | Capacity building on identified gaps for all faculty of seven departments (A maximum of 5 (five) faculty from each of the seven departments giving a total of 35 faculty) | [28 empty] | 330000 |  |  | Center Team
Activity 1:Training on data visualization | Training on data visualization (estimate to train 30 persons) | [28 empty] | 7356 | 10000 |  | Center Team | bar: Q1 2024 Jan
Sub-Action 1d: International Accreditation
Activity 1: Self-assessment and accreditation by APHEA | Conduct self-assessment for accreditation by APHEA of 2 MSc programs | [28 empty] | 44500 | 100000 |  | Center Team | bar: Q1 2024 Jan to Q1 2024 Mar
Activity 2: International Accreditation | Engage APHEA to conduct international accreditation for two MSc programmes | [28 empty] | 100000 | 400000 | bar: Q1 2024 Jan to Q1 2024 Mar; Q3 2024 Jul to Q4 2024 Dec
Action 2: DLI Action : Applied research
Sub-Action 2a: Support applied research
Activity 1: Training workshop on statistical packages on research (R and Nvivo) | Conduct trainings on R, STATA, Epi Info, SPSS etc for staff and students to acquire skills on data anaysis | [28 empty] | 53334 | 18000 |  | Center Team | bar: Q1 2024 Mar
Activity 2:Provide seed grant to faculty for a pilot study on competitive bases | Grants will be awarded to research clusters to carry out pilot/ formative research based on merit of the proposals. | [28 empty] | 25000 |  |  | Center Team
Activity 3: Procurement of software for computer lab (STATA, SPSS, N-vivo, Madonna, TreeAge | Statistical softwares for quantitative and qualitative research will be procured and installed on the computers in the computer laboratory | [28 empty] | 5200 |  |  | Center Team | bar: Q1 2024 Jan to Q1 2024 Mar
Activity 4: Publish research output | Manuscripts will be written from our research output and published in high impact journals. | [28 empty] | 10000 | 300000 |  | Center Faculty
Sub-Action 2b: Upgrading Research Labs
Activity 1: Upgrade the skill acquisition/demostration in the College of Health sciences, AKTH | Nursing skill acquisition lobarory wil be upgraded to provide teaching and research capacity | [28 empty] | 391778 |  |  | Center Team | bar: Q2 2024 Apr to Q2 2024 Jun
Activity 2: Upgrading Anthropometrics laboratory | Establish an Anthropometric laboratory for clinical research | [28 empty] | 50000 |  |  | Center Team | bar: Q1 2024 Jan to Q1 2024 Mar
Sub-Action 2c: Community engagement for research
Activity 1: Mapping and community diagnosis of Tofa LGA | Determine health needs of Yanako community and set up interventions with community participation | [28 empty] | 20640 |  |  | Center Team & Community Medicine Dept | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 2: Community engagement activities at Tofa community | Conduct community activities for the improvement of MCH | [28 empty] | 24390 |  |  | Center Team & Community Medicine Dept
Action 3: DLI Action: Partner collaboration
Activity 1: Dan koloudo: Training of 2 staff and procurement of equipment and consumables | To support Dan koloudo University Maradi Niger Republic to establish a histopathology laboratory by training staff and procuring equipment |  | Dankoloudo University Maradi Niger Republic | [26 empty] | 86834 |  |  | Center Team & Partner | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 2: Lighthouse: Nutrition project | To partner with Lighthouse to improve nutrition in 2 communities in Kano State |  | Lighthouse contribution | [26 empty] | 52909.4 |  |  | Center Team & Partner
Activity 3; Kano State Independent Research and Training Center (KIRTC) maternal health project | To partner with KIRTC to conduct a digital platform to improve maternal Health access in Kano State |  | KIRC contribution | [26 empty] | 200000 |  |  | Center Team & Partner
Activity 4: RAISE Foundation emergency obstetric care project | To partner with RAISE Foundation to improve Maternal Newborn health in Niger state |  | RAISE Foundation | [26 empty] | 13334 | 63000 |  | Center Team & Partner | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 5: Women Organization for Relief and Empowerment | Partner with WORE to organize activities towards providing relief and empowerment to vulnerable women in Kano State |  | WORE Organization | [26 empty] | 20000 |  |  | Center Team & Partner
Activity 6: Capacity building for healthcare workers of Jigawa State | As part of the MoU with Jigawa state, capacity building on maternal newborn health will be conducted for health care workers in the state |  | Jigawa State | [26 empty] | 30000 | 90000 |  | Center Team & Partner
Activity 7: Community outreach Activities with Partners | Partner with other organizations to conduct outreach activities | [28 empty] | 80000 |  |  | Center Team & Partner
Sub-Action 3b: Internship
Activity 1: Two (2) staff undertake one month placement in national industrial sectoral partners | Two staff from our collaborating departments will be identified and supported to undertake a month internship in a relevant industry/ partner organization nationally | [28 empty] | 21326 | 4000 |  | Center Team
Activity 2: Support Two (2) staff to undertake one month placement in regional industrial sectoral partners | Two staff from our collaborating departments will be identified and supported to undertake a month internship in a relevant industry/ partner organization regionally | [28 empty] | 57880 | 3000 |  | Center Team
Activity 3: Support for student internship local | Students will be supported to undertake a month internship in a relevant industry/ partner organization based in Kano (estimate to support 40 national students) | [28 empty] | 8200 | 75000 |  | Center Team
Activity 4: Support for student internship regional | Students will be supported to undertake a month internship in a relevant regional industry/ partner organization (estimate to support 12 regional students) | [28 empty] | 48000 | 15000 |  | Center Team
Sub-Action 3c: Collaborative research
Activity 1: Seed grants for collaborative research with partners | To support 5 faculty to conduct pilot, findings of which will support the Center to get more grants for sustainability | [28 empty] | 25000 | 249314 |  | Center Team | bar: Q3 2024 Aug
Activity 2: Develop and test local therapeutic food for children under-5 with Dala Foods and Jigawa State Governement | To develop food suppliments to address malnutrition in Jigawa State | [28 empty] | 100000 |  |  | Center Team &Jigawa State
Sub-Action 3d: Community outreaches
Activity 1: Conduct community outreach in Jigawa State | To support Jigawa State to provide health awareness in communities in Jigawa State as part of our collaboartion |  | Jigawa State | [26 empty] | 20000 |  |  | Jigawa State and Center Team
Acttivity 2: Establishing community e-health in collaboration with E-DOKTA | E-health app will be developed to aid community health |  | E-Dokta | [26 empty] | 30650 |  |  | E-Dokta and Center Team
Action 4: DLI Action:Policy implimentation
Sub-Action 4a: Policy engagement
Activity 1: Develop policy briefs and engage policy makers | The Center will develop policy briefs and engage policy makers through advocay and dialogue. | [28 empty] | 38870 | 13500 |  | Center team
Action 5: \DLI Action:Improved enviroment
Sub-Action 5a: Construction of student hostel
Activity 1: Completion of student hostel | Construction of students' hostel completed | [28 empty] | 250976 | 600000 |  | Procurement Officer | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 2: ESMP activities | To conduct ESMP activities including training of staff | [28 empty] | 78000 |  |  | Center Team | bar: Q1 2024 Jan to Q2 2024 Jun
Conduct ESMP implementation audit for all construction activities including funding. | The Center will conduct implementaiton audit for the construction of international students hostel | [28 empty] | 6000 |  |  | Safeguards officer | bar: Q1 2024 Jan to Q2 2024 Jun
o Provide adequate signage around work areas/institution premises. o | The Center will provide signage around the institution premises | [28 empty] | 8000 |  |  | Safeguards officer | bar: Q1 2024 Jan to Q2 2024 Jun
o Implement / Administer the worker's code of conduct as per the ESMP provision | The Center will continue to administer the workers code of conduct | [31 empty] | Safeguards officer | bar: Q1 2024 Jan to Q2 2024 Jun
Sub-Action 5b: Creation of learning infrastructure
Activity 1: Creation of C-Code studio | Equipment procurred for the digital studio to aid establishing digital education | [28 empty] | 57000 |  |  | Center Team | bar: Q1 2024 Jan to Q2 2024 Jun
Action 6: \DLI Action: Management
Sub-Action 6a: Capacity building for improved management
Activity 1: Capacity building for administrative staff ( regional) | The center shall organize short trainng courses as well as support travels (regionally) for training for its staff to enhance center logistic and administrative support | [28 empty] | 50850 | 31000 |  | Center Team
Activity 2: Capacity building for administrative staff (local, national) | The center shall organize short trainng courses as well as support travels (local & nationally) for training for its staff to enhance center logistic and administrative support | [28 empty] | 13540 | 10000
Activity 3:Training on project management for DD Training Safeguard Officer | To improve ACEPHAP project management | [28 empty] | 23450 |  |  | Center Team | bar: Q1 2024 Jan to Q2 2024 Jun
Sub-Action 6b: Project coordination
Activity 1: Center management | Manage the day to day activities of the Center and conduct montlhy meeting in pursuance of set objectives and goals | [28 empty] | 14878 |  |  | Center Team
Activity 2: Attend ACE regional meetings | The Center Team shall attend biannual ACE Impact AAU meeting | [28 empty] | 72000 |  |  | Center Team | bar: Q2 2024 Apr; Q4 2024 Nov
Activity 3: Sectoral Advisory Board meeting | The SAB would meet to discuss the Center's continuous engagement with the sector, avenues for collaboration and support | [28 empty] | 38670 |  |  | Center Team | bar: Q2 2024 Jun
Activity 4: International Scientific Advisory Board meeting: | The ISAB would meet to discuss the Center's continuous engagement and partnership for academic excellence and to also pursue research opportunities. | [28 empty] | 38670 |  |  | Center Team | bar: Q2 2024 Jun
Sub-Action 6c: Finance and audit
Activity1: Produce timely fiduciary reports | The center leadership in conjuction with the accounts and audit department shall see to timely processing of fiduciary reports | [28 empty] | 350 | 15000 |  | Center Team | bar: Q2 2024 Jun; Q4 2024 Dec
Activity2:Preparation of quarterly internal audit reports of financial activities of 2022. | The center leadership in conjuction with the accounts and audit department shall see to timely processing of quartely audit report of center financial activities | [28 empty] | 150 | 15000 |  | Center Team | bar: Q1 2024 Mar; Q2 2024 Jun; Q3 2024 Sept; Q4 2024 Dec
Activity 3:Produce Half yearly internal audit report | The center leadership in conjuction with the accounts and audit department shall see to timely processing of center half yearly audit report | [28 empty] | 150 | 15000 |  | Center Team | bar: Q2 2024 Jun; Q4 2024 Dec
Activity 4:Produce external audit report and procurement audit | The center leadership in conjuction with the accounts and audit department shall see to timely processing of center external audit report | [28 empty] | 5000 | 15000 |  | Center Team | bar: Q1 2024 Mar; Q2 2024 Jun; Q3 2024 Sept; Q4 2024 Dec
Activity 5:Compile timely financial and procurement reports and upload on the center website | The center leadership in conjuction with the accounts and audit department shall see to timely processing and compiling of center procurement reports and ensure its timly uploading to center website | [28 empty] | 150 | 15000 |  | Center Team | bar: Q1 2024 Mar; Q2 2024 Jun; Q3 2024 Sept; Q4 2024 Dec
Activity 6: Preparation of external audit reports of procurement activities of 2023/24. | External audit will be done to ensure the adherance of the Nigerian audit process | [28 empty] | 120 | 15000 |  | Center Team | bar: Q1 2024 Mar; Q2 2024 Jun; Q3 2024 Sept; Q4 2024 Dec
Action 7: \DLI Institutional impact
Sub-Action 7a: Improving global visibility of the university
Activity 1: Conduct GAP analysis for BUK international accreditation | The center shall support the university in an effort towards univesit GAP analysis towards attainment of international accreditation | [28 empty] | 50000 | 75000 |  | University DLI 7 Lead, Center Team | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 2: Conduct self-evaluation as part of international accreditation | The center shall support the university in an effort towards university self evaluation proceedings towards attainment of international accreditation | [28 empty] | 50000 | 75000 |  | University DLI 7 Lead, Center Team | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 3: Conduct institutional accreditation | Quality Assurance Agency has been identified for the accreditation | [28 empty] | 100000 | 200000 |  | University DLI 7 Lead, Center Team | bar: Q2 2024 Jun
Activity 4: Strenthened the Alumni Advancement Office | To have a functional Alumni Advancement Office | [28 empty] | 1000 |  |  | University DLI 7 Lead, Center Team | bar: Q2 2024 Jun
Activity 5: Strenthening the public Affairs Directorate | To have a strenthened public Affairs unit for optimal communication to and fro the university | [28 empty] | 4416 |  |  | University DLI 7 Lead, Center Team | bar: Q2 2024 Jun
Sub-Action 7b: Strentgthening University innovation and entrepreneurship ecosystem (DLI 5.3)
Activity 1: M 1.1. Establish University innovation/entrepreneurship ecosystem through the strengthening of the Technology Transfer Office | University innovation and emtrepreneurship ecosystem will be strengthened througy strengthening TTO, training of faculty and signing MoU with incubation centers | [28 empty] | 21000 | 100000 |  | Center Team, DLI 5.3 Focal person | bar: Q1 2024 Jan to Q2 2024 Jun
Activity 2: M 2.1. An innovation and entrepreneurship curriculum developed and offered (for at least 1 term) for students and faculty members of each Center. | Develop/ review/ adopt an entrepreneurship curriculum for PG students and Faculty | [28 empty] | 46500 |  |  | Center Team, DLI 5.3 Focal person | bar: Q1 2024 Jan to Q1 2024 Mar
Activity 3: M 3.2. Establish faculty consulting business development office, including establishment of a mentoring program for start-ups and/or entrepreneurs | Establish a consulting business development office and develop its operational guideline | [28 empty] | 9200 |  |  | Center Team, DLI 5.3 Focal person | bar: Q2 2024 May to Q3 2024 Sept
Sub-Action 7c: Communication
Activity 1: Engagement of media specialist for increased visibility of ACEPHAP activities | The Center will engage media specialist to produce media tools for increased visibility of ACEPHAP activities | [28 empty] | 10317 |  |  | Center Team
[29 empty] | Total | 3264581.4 | 2656814
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Under Action 1 (Quality Education): o please include the estimated number of new master’s and PhD students that will be enrolled in 2024 o under row 16, please include the estimated number of short courses and a rough estimate to how many will be trained · Add a timeline for row 33 (community engagement activities at Tofa community) · Please fill in cell A37 (currently empty, should be describe activity 3 under Action 3 – Partner collaboration) · In rows 45 and 46, please include the estimated number of internships to be completed. It is great to see two separate line items for national vs. regional internships.
Note on A59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It is good to see that you include “ESMP activities” in row 59 related to the construction of the student hostel. Please consider adding the following specific activities to provide more detail/guidance: o Conduct ESMP implementation audit for all construction activities including funding. o Provide adequate signage around work areas/institution premises. o Implement / Administer the worker's code of conduct as per the ESMP provision o Provide for transportation to construction sites if far from the university campus
Note on A82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Under the section for DLI 7 (starting at row 79): o Please include activities related to milestone 3 under DLR 7.5: Strengthening the University Alumni/Advancement Office o Please include activities related to milestone 5 under DLR 7.5: Strengthening the University Public Affairs Directorate

## Sheet2
53902
4444
153407
188570
18670
330000
248750
7356
44500
53334
25000
5200
10000
391778
50000
20640
24390
86834
52909.4
200000
13334
30000
100000
21326
57880
8200
48000
25000
100000
20000
30650
38870
78000
57000
50850 | #ERROR!
13540
23450
14878
72000
38670
38670
350
150
150
5000
150
120
50000
50000
100000
21000
46500
9200
10317
3142939.4